## Table 1
NASORLO MODERNIZATION EFFORTS, INITIATIVES
Land & Water Conservation Fund State Assistance Program
Efficiencies, Updates and Modernization Initiatives
2018 Priorities | Priority | Proposal and LWCF Section Reference | Summary Rationale | Supporter | Timetable | Status | 03.16.2018 Meeting Comments/Notes | 3.16.2018 Action | Action Updates
1 | High | New Provision – Authorize State Program Administrative Funding 54 §200305 (a) Previous: 460/-8(a), -8(b)(4), and 8(e)(3) | Most Federal financial assistance programs permit the use of grant funds for administrative costs on a limited basis. Regular funding to states is needed to help cover costs to meet federal requirements including ensuring fund-assisted sites are regularly inspected and remain open for public outdoor recreation uses in perpetuity as mandated by the Act. This will enhance the Federal/state partnership to address this unfunded mandate. Examples of programs permitting administrative funding: Recreational Trails – 7%; Forest Legacy – <15%; EPA Water grants. | NPS NASORLO |  | Need legislative change. As part of 2016 Annual Meeting experts from DOI will present on process for indirect-rate | #1 priority. This items was recently discussed during a visit to DC. DC appeared to be generally supportive. Suggested to add language when it is reauthorized. Biggest funding need for states relateds to compliance and inspections, not current grant rounds. | Talk to Doug about strategy… should we consider surveying states or is that too risky? Concern if we show how far behind states are we could lose current program. Current grant program fine… issue with compliance on past due inspections. | Proposal for up to 10% of annual apportionment or $200,000 has be drafted and forwarded to NPS
2 | High | Certificate of Apportionment New Provision – 54, §200305 (a) | Before states can spend or grant LWCF assistance, the Secretary of Interior issues a Certificate of Apportionment and notifies states and territorial governments of their respective fund amounts. LWCF State Assistance Program is a formula grant, therefore requiring no special review or oversight. Earlier distribution of apportionments translates to quicker obligations of funds for outdoor recreation projects at the local level. | NASORLO |  | Included in our legislative meetings in Spring 2016 and in follow up letters. | Keep
3 | High | Conversions: LWCF Manual - Amend Chapter 8E – authorize state administrative approval of small conversions and reduce environmental and 106 requisites | Though LWCF is intended to protect sites in perpetuity, there are circumstances when conversions are minor. While minor/small conversions are less complex, though are subject to the same federal requirements as large/major conversions. Small and large conversions require NPS review and approval. To expeditiously resolve minor cases, and to allow LWCF site sponsors to be less encumbered by laborious processes, we recommend that LWCF State Liaison Officers be given authority to manage and approve small conversions. Qualifying small conversions are no more than 10 percent of the 6(f) protected area. Small conversions are categorical exclusions - address current environmental and Section 106 requirement. | NASORLO |  | NPS considers this to require a legislative change. Does it? We should research language for other delegated programs. | New language should be included in draft of new manual. | Cleve will review in draft manual as soon as he receives it. | Given ongoing capacity issues at NPS, Modernization Committee recommends the following considerations to expedite conversions: 1) Once a conversion has been submitted to NPS for review, NPS will have 180 days to respond. If no response, then conversion is approved. or 2) Delegate the Authority to States to resolve all conversions.
4 | NEW - HIGH | Conversions: LWCF Manual - Amend Chapter 8E – Given ongoing capacity issues at NPS, Modernization Committee recommends the following considerations to expedite conversions: 1) Once a conversion has been submitted to NPS for review, NPS will have 180 days to respond. If no response, then conversion is approved. or 2) Delegate the Authority to States to resolve all conversions. | Though LWCF is intended to protect sites in perpetuity. To expeditiously resolve all cases, and to allow LWCF site sponsors to be less encumbered by laborious processes, we recommend that LWCF State Liaison Officers be given authority to manage and approve small conversions. Qualifying small conversions are no more than 10 percent of the 6(f) protected area. Small conversions are categorical exclusions - address current environmental and Section 106 requirement. | Modernization Committee |  | not submitted for consideration | New language should be included in draft of new manual.
5 | NEW - HIGH | Boundaries 6(f)(3) are the basis of all conversions. Establish a 6(f) advisory committee to work with NPS on a reasonable and measured determination of boundaries when uncertain, ambiguous, incomplete and or non existent boundaries exist in the inventory of previously fund assisted projects | From 1965 to 1978 there was no LWCF guidance for what was to be the project boundary or how that boundary was to be identified. Since 1978 there has been a wide degree of variation of how boundaries have been recorded. When these assisted sites are revisited during conversions, the need to identify the project boundary is paramount for the rest of the process to proceed, however States and NPS dissagree on the most appropriate means of resolving boundary uncertainty. NPS wants all of the land in public ownership at the time of award without regard to practicality and expectations of applicants at the time of award. States see the implications first hand and given their perpetual stewardship obligations see the need for a more reasoned and measured approach to resolving indistinct project boundaries | NASORLO |  | proposed to NPS | One of four white papers submitted to NPS for consideration
6 | High | Amend Provision – Clarify conversion definition to allow certain temporary non- conforming uses of 6(f) protected sites. Previous: 460/-8(f)(3) | Embedded in 1992 Appropriations act is a restriction on non-conforming recreational activities within LWCF assisted/protected areas (known as LWCF 6(f) areas). Conditions arise where temporary non-recreation activities may occur within LWCF 6(f) protected areas. If the activity lasts beyond 6 months a conversion is triggered. Conversions are permanent. Need to clarify that certain temporary uses can be allowed for longer period. Changing rule to 3 years acknowledges conditions of park construction; limitations imposed by permits; eliminates land conversion requirements and associated costs; and provide greater flexibility to States to manage the LWCF Program. | NPS NASORLO |  | This is under active discussion. NASORLO supports moving to 3 years without doing further analysis. A federal register process is required and NPS should initiate one. | Try to revise in new manual. Question if NPS has the authority to change? | Follow up discussion with Emily.
7 | High | New Provision - Authorize the use of non-LWCF Federal funds for replacement property where Federal action is causing the 6(f) conversion Previous: 460/-8(f)(1) | Local and state grant sponsors are unduly burdened by having to satisfy a conversion replacement caused by a Federal action (e.g. highway realignment) due to the prohibitions of the use of Federal dollars to help pay for replacement property. Amendment would allow Federal money to be used to mitigate the Federal action. | NPS NASORLO |  |  | DOT could buy property. Property using T.E. funds highlighted to recreation uses as long as recreation. | Talk to NPS Directly - good committee topic. Cleve will review in draft manual.
8 | High | LWCF Manual - Amend Chapter 2.A.4. | Require states to create a digital GIS spatial database of all local and state LWCF properties and encourage creation of digital database of all publicly-owned outdoor recreation areas and parks. A digital record of LWCF sites will modernize and create a historical record of Congress’s investments in state and local LWCF sites. Today, digital records have been created by 25 states, though no detailed comprehensive GIS- based inventory exists. Database creation would be an administrative or SCORP related activity and 50% cost recoverable. | NASORLO |  | Active work on this. Will have session at our annual meeting. | PAD US initiative that Susan was leading. | Jan will look at the manual and research the background on this one.
9 | NEW / Medium | LWCF Manual - Amend Chapter 5.B.2.g - Limits of Valuation | Limits of valuation for match needs further clarification and the opportunity presents itself during manual revision and review under way. There are states who believe they are unreasonably being restricted in using bargain sale or excess land value as match for eligible proejcts. | NASORLO
10 | NEW / Medium | Establish a cloud based file transfer and storage system where NPS staff can maintaine one folder per state. In this folder will reside sub folders for each project submitted for review / approval for new funding and for each project experiencing some degree of compliance difficulties | Email is an ineffecient means of sharing files and communicating key aspects of projects needing review and action. In many cases states have submitted project related files only to find that the emails on the receiving end become burried, or worse, are shunted to "Junk" folders and not seen in a timely manner if at all. Modern technology has delivered the solution to this in the form of mutually shared - cloud based folders in which all related project files can be saved, shared, reviewed and acted upon without having to search one's "inbox" for recent activity. Email then would be simply a means of informing either party that new files await review. | NASORLO | Could be implemented imediately | Suggested at Reno NASORLO meeting
11 | Medium | LWCF Manual - Amend Chapter 2.A.7. Previous: Amend Section 6(d) of LWCF Act, SCORP | The State Comprehensive Outdoor Recreation Plan (SCORP) is required to maintain eligibility for LWCF assistance. SCORP are required every 5 years. Shifting SCORPs to every 10 years, with the option of a 5 year update due to significant statewide changes, follow today’s planning cycles and objectives. | NASORLO |  |  | Follow up with NPS
12 | Medium | LWCF Manual – Amend Chapter 2.C.6. | While states are given authority to screen and select acquisition and construction projects for LWCF funding, SCORP planning grants are subject to funding limits. This limitation does not give states the discretion to determine the funding level desired to support planning activities and reduces SCORP elements critical for directing future LCWF investments where they are most needed and effective. | NASORLO |  |  | Follow up with NPS
13 | Medium | LWCF Manual – Administrative amendment for types of planning projects Chapter 2.C.5.d. | Special planning studies are eligible for LWCF assistance, though NPS guidance does not allow the use of LWCF to establish economic impacts of parks. Amend this administrative rule to allow economic impact analyses once every 10 years to demonstrate the economic contribution/value of parks in states and/or urban areas. Specifically address using LWCF planning grants, and/or administrative funds, for the purposes of creating GIS databases of LWCF-assisted project sites including electronic databases of LWCF projects, past and present. | NASORLO |  |  | Follow up with NPS
14 | Medium | Amend Provision – Permit the use other Federal funds in a LWCF project 54 §200305 (a) Previous: 460/-8(c) and 8(f)(1) | Chapter 5 Cost Principles: 5. Federal matching and supplemental programs. Section 6(f) of the LWCF Act prohibits the use of other federal financial assistance to pay the state or local matching share of a LWCF grant. However, in those instances where the statutory provisions of a subsequent federal grant-in-aid program explicitly allow recipients to use such assistance to match LWCF funds as in Community Development Block Grants (CDBG) and through the Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users (SAFETEA-LU) Act. Section 6(f)(1) of the LWCF Act is superseded and a matching arrangement is permissible. | NPS NASORLO |  | Chapter 5 Cost Principles: 5. Federal matching and supplemental programs. Section 6(f) of the LWCF Act prohibits the use of other federal financial assistance to pay the state or local matching share of a LWCF grant. However, in those instances where the statutory provisions of a subsequent federal grant-in-aid program explicitly allow recipients to use such assistance to match LWCF funds as in Community Development Block Grants (CDBG) and through the Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users (SAFETEA-LU) Act. Section 6(f)(1) of the LWCF Act is superseded and a matching arrangement is permissible. | Need to be specific regarding what federal funds should be used in conjunction with LWCF. RTP can be used for LWCF. | Doug B. volunteered to look into this one to research and be more specific. | There are too many other federal programs to create a comprehensive menu of available eligible LWCF match grants. Guidance from NPS was to research each and inquire of NPS if no clear guidance exists.
15 | Medium | Amend Provision – Permit “incidental costs” associated with and land acquisition 54 §200305 (a) Previous: 460/-8(e)(1) | Currently incidental costs associated with land acquisition, such as title work, appraisals, and closing expenses, are not allowable expenses. Such expenses are integral to acquisition projects and allowable in most if not all other Federal financial assistance program. For example, under USFWS and Forest Legacy grant programs, costs associated with land acquisition are allowable, i.e., appraisal feeds, boundary survey fees, title search and insurance costs, closing costs (attorney fees, etc.), Phase I ESA fees, and staff time. And, Forest Legacy program funds also cover a portion of these types of land acquisition related functions. | NPS NASORLO |  |  |  | Ask NPS why not?
16 | Medium | Amend LWCF Manual changing land appraisal standards Chapter 4.D.7.c. | Only Uniform Appraisal Standards of Federal Land Acquisitions (UASFLA “Yellow Book”) may be used in LWCF acquisition projects. For Wildlife Restoration Grants (P/R) administered by the USF&WS, real estate appraisals may meet the Uniform Standards of Professional Appraisal Practice (USPAP) [Standards 1 & 2] –changed from Yellow Book under program rules. | NASORLO |  |  | Believe NPS is working on this. | Confirm with NPS that they are working on this.
17 | Medium | Amend Provision – Eliminate authority for funding “sheltered facilities” 54 §200305 (e)(3) Previous: 460/-8(e)(2) | While otherwise generally a prohibited use of LWCF funding, the Act was amended in 1976 to permit funding, of ‘sheltered facilities” on a limited bases in areas of severity of climatic conditions affecting certain areas and states. Removing the provision does not prevent project sponsors from using their own funds to shelter any outdoor recreation activity with NPS approval. | NPS NASORLO |  | This seems like it is an easy fix. How do we make this happen? | Discussion around the purpose of this one. Believe it is to make it fair for all states and consistent. Need to look at manual for opportunities to clean up language. | Discuss with NPS
18 | Medium | Amend Provision – Eliminate wetland areas consideration as equivalent usefulness for conversion replacement property. 54 §200305 (f)(3) Previous: 460/-8(f)(3) | In spite of the waiver for the recreation usefulness standards, it is still difficult to use wetlands as conversion replacement property because they rarely satisfy the at least equal value requirement. In addition, wetlands should not necessarily be thought of as easy replacement for outdoor recreation facilities. | NPS NASORLO |  | This seems like it is an easy fix. How do we make this happen? | Conversation center around active versus passive recreation… Decided to keep on the list and continue conversation - explore options.
19 | Medium | Eliminate Provision – SCORP Wetland planning requirement 54 §200305 (d)(4) Previous: 460/-8(d) | These provisions for wetlands were added to the LWCF in the 1988 amendments. Wetlands protections and other requirements enacted subsequently have made the wetland component of the LWCF State assistance program redundant. | NPS NASORLO |  | This seems like it is an easy fix. How do we make this happen? | Seems unrelated to SCORP. Agreement that this should be fixed. Not sure why this provision was added. Confusion about 460/-8(d). | Ask Doug about "460/-8(d). Discuss with NPS.
20
21
22

## Sheet1
1 | High | New Provision – Authorize State Program Administrative Funding 54 §200305 (a) Previous: 460/-8(a), -8(b)(4), and 8(e)(3) | Most Federal financial assistance programs permit the use of grant funds for administrative costs on a limited basis. Regular funding to states is needed to help cover costs to meet federal requirements including ensuring fund-assisted sites are regularly inspected and remain open for public outdoor recreation uses in perpetuity as mandated by the Act. This will enhance the Federal/state partnership to address this unfunded mandate. Examples of programs permitting administrative funding: Recreational Trails – 7%; Forest Legacy – <15%; EPA Water grants.
2 | High | Certificate of Apportionment New Provision – 54, §200305 (a) | Before states can spend or grant LWCF assistance, the Secretary of Interior issues a Certificate of Apportionment and notifies states and territorial governments of their respective fund amounts. LWCF State Assistance Program is a formula grant, therefore requiring no special review or oversight. Earlier distribution of apportionments translates to quicker obligations of funds for outdoor recreation projects at the local level.
3 | High | Conversions: LWCF Manual - Amend Chapter 8E – authorize state administrative approval of small conversions and reduce environmental and 106 requisites | Though LWCF is intended to protect sites in perpetuity, there are circumstances when conversions are minor. While minor/small conversions are less complex, though are subject to the same federal requirements as large/major conversions. Small and large conversions require NPS review and approval. To expeditiously resolve minor cases, and to allow LWCF site sponsors to be less encumbered by laborious processes, we recommend that LWCF State Liaison Officers be given authority to manage and approve small conversions. Qualifying small conversions are no more than 10 percent of the 6(f) protected area. Small conversions are categorical exclusions - address current environmental and Section 106 requirement.
4 | NEW - HIGH | Conversions: LWCF Manual - Amend Chapter 8E – Given ongoing capacity issues at NPS, Modernization Committee recommends the following considerations to expedite conversions: 1) Once a conversion has been submitted to NPS for review, NPS will have 180 days to respond. If no response, then conversion is approved. or 2) Delegate the Authority to States to resolve all conversions. | Though LWCF is intended to protect sites in perpetuity. To expeditiously resolve all cases, and to allow LWCF site sponsors to be less encumbered by laborious processes, we recommend that LWCF State Liaison Officers be given authority to manage and approve small conversions. Qualifying small conversions are no more than 10 percent of the 6(f) protected area. Small conversions are categorical exclusions - address current environmental and Section 106 requirement.
5 | NEW - HIGH | Boundaries 6(f)(3) are the basis of all conversions. Establish a 6(f) advisory committee to work with NPS on a reasonable and measured determination of boundaries when uncertain, ambiguous, incomplete and or non existent boundaries exist in the inventory of previously fund assisted projects | From 1965 to 1978 there was no LWCF guidance for what was to be the project boundary or how that boundary was to be identified. Since 1978 there has been a wide degree of variation of how boundaries have been recorded. When these assisted sites are revisited during conversions, the need to identify the project boundary is paramount for the rest of the process to proceed, however States and NPS dissagree on the most appropriate means of resolving boundary uncertainty. NPS wants all of the land in public ownership at the time of award without regard to practicality and expectations of applicants at the time of award. States see the implications first hand and given their perpetual stewardship obligations see the need for a more reasoned and measured approach to resolving indistinct project boundaries
6 | High | Amend Provision – Clarify conversion definition to allow certain temporary non- conforming uses of 6(f) protected sites. Previous: 460/-8(f)(3) | Embedded in 1992 Appropriations act is a restriction on non-conforming recreational activities within LWCF assisted/protected areas (known as LWCF 6(f) areas). Conditions arise where temporary non-recreation activities may occur within LWCF 6(f) protected areas. If the activity lasts beyond 6 months a conversion is triggered. Conversions are permanent. Need to clarify that certain temporary uses can be allowed for longer period. Changing rule to 3 years acknowledges conditions of park construction; limitations imposed by permits; eliminates land conversion requirements and associated costs; and provide greater flexibility to States to manage the LWCF Program.
7 | High | New Provision - Authorize the use of non-LWCF Federal funds for replacement property where Federal action is causing the 6(f) conversion Previous: 460/-8(f)(1) | Local and state grant sponsors are unduly burdened by having to satisfy a conversion replacement caused by a Federal action (e.g. highway realignment) due to the prohibitions of the use of Federal dollars to help pay for replacement property. Amendment would allow Federal money to be used to mitigate the Federal action.
8 | High | LWCF Manual - Amend Chapter 2.A.4. | Require states to create a digital GIS spatial database of all local and state LWCF properties and encourage creation of digital database of all publicly-owned outdoor recreation areas and parks. A digital record of LWCF sites will modernize and create a historical record of Congress’s investments in state and local LWCF sites. Today, digital records have been created by 25 states, though no detailed comprehensive GIS- based inventory exists. Database creation would be an administrative or SCORP related activity and 50% cost recoverable.
9 | NEW / Medium | LWCF Manual - Amend Chapter 5.B.2.g - Limits of Valuation | Limits of valuation for match needs further clarification and the opportunity presents itself during manual revision and review under way. There are states who believe they are unreasonably being restricted in using bargain sale or excess land value as match for eligible proejcts.
10 | NEW / Medium | Establish a cloud based file transfer and storage system where NPS staff can maintaine one folder per state. In this folder will reside sub folders for each project submitted for review / approval for new funding and for each project experiencing some degree of compliance difficulties | Email is an ineffecient means of sharing files and communicating key aspects of projects needing review and action. In many cases states have submitted project related files only to find that the emails on the receiving end become burried, or worse, are shunted to "Junk" folders and not seen in a timely manner if at all. Modern technology has delivered the solution to this in the form of mutually shared - cloud based folders in which all related project files can be saved, shared, reviewed and acted upon without having to search one's "inbox" for recent activity. Email then would be simply a means of informing either party that new files await review.
11 | Medium | LWCF Manual - Amend Chapter 2.A.7. Previous: Amend Section 6(d) of LWCF Act, SCORP | The State Comprehensive Outdoor Recreation Plan (SCORP) is required to maintain eligibility for LWCF assistance. SCORP are required every 5 years. Shifting SCORPs to every 10 years, with the option of a 5 year update due to significant statewide changes, follow today’s planning cycles and objectives.
12 | Medium | LWCF Manual – Amend Chapter 2.C.6. | While states are given authority to screen and select acquisition and construction projects for LWCF funding, SCORP planning grants are subject to funding limits. This limitation does not give states the discretion to determine the funding level desired to support planning activities and reduces SCORP elements critical for directing future LCWF investments where they are most needed and effective.
13 | Medium | LWCF Manual – Administrative amendment for types of planning projects Chapter 2.C.5.d. | Special planning studies are eligible for LWCF assistance, though NPS guidance does not allow the use of LWCF to establish economic impacts of parks. Amend this administrative rule to allow economic impact analyses once every 10 years to demonstrate the economic contribution/value of parks in states and/or urban areas. Specifically address using LWCF planning grants, and/or administrative funds, for the purposes of creating GIS databases of LWCF-assisted project sites including electronic databases of LWCF projects, past and present.
14 | Medium | Amend Provision – Permit the use other Federal funds in a LWCF project 54 §200305 (a) Previous: 460/-8(c) and 8(f)(1) | Chapter 5 Cost Principles: 5. Federal matching and supplemental programs. Section 6(f) of the LWCF Act prohibits the use of other federal financial assistance to pay the state or local matching share of a LWCF grant. However, in those instances where the statutory provisions of a subsequent federal grant-in-aid program explicitly allow recipients to use such assistance to match LWCF funds as in Community Development Block Grants (CDBG) and through the Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users (SAFETEA-LU) Act. Section 6(f)(1) of the LWCF Act is superseded and a matching arrangement is permissible.
15 | Medium | Amend Provision – Permit “incidental costs” associated with and land acquisition 54 §200305 (a) Previous: 460/-8(e)(1) | Currently incidental costs associated with land acquisition, such as title work, appraisals, and closing expenses, are not allowable expenses. Such expenses are integral to acquisition projects and allowable in most if not all other Federal financial assistance program. For example, under USFWS and Forest Legacy grant programs, costs associated with land acquisition are allowable, i.e., appraisal feeds, boundary survey fees, title search and insurance costs, closing costs (attorney fees, etc.), Phase I ESA fees, and staff time. And, Forest Legacy program funds also cover a portion of these types of land acquisition related functions.
16 | Medium | Amend LWCF Manual changing land appraisal standards Chapter 4.D.7.c. | Only Uniform Appraisal Standards of Federal Land Acquisitions (UASFLA “Yellow Book”) may be used in LWCF acquisition projects. For Wildlife Restoration Grants (P/R) administered by the USF&WS, real estate appraisals may meet the Uniform Standards of Professional Appraisal Practice (USPAP) [Standards 1 & 2] –changed from Yellow Book under program rules.
17 | Medium | Amend Provision – Eliminate authority for funding “sheltered facilities” 54 §200305 (e)(3) Previous: 460/-8(e)(2) | While otherwise generally a prohibited use of LWCF funding, the Act was amended in 1976 to permit funding, of ‘sheltered facilities” on a limited bases in areas of severity of climatic conditions affecting certain areas and states. Removing the provision does not prevent project sponsors from using their own funds to shelter any outdoor recreation activity with NPS approval.
18 | Medium | Amend Provision – Eliminate wetland areas consideration as equivalent usefulness for conversion replacement property. 54 §200305 (f)(3) Previous: 460/-8(f)(3) | In spite of the waiver for the recreation usefulness standards, it is still difficult to use wetlands as conversion replacement property because they rarely satisfy the at least equal value requirement. In addition, wetlands should not necessarily be thought of as easy replacement for outdoor recreation facilities.
19 | Medium | Eliminate Provision – SCORP Wetland planning requirement 54 §200305 (d)(4) Previous: 460/-8(d) | These provisions for wetlands were added to the LWCF in the 1988 amendments. Wetlands protections and other requirements enacted subsequently have made the wetland component of the LWCF State assistance program redundant.